## Costs Summary
Salaries | 137800
Equipment, Software & Hosting | 6700
Operational Fees | 5500
Total | 150000

## Resource Plan
[5 empty] | Resources | 19500 | 19500 | 19500 | 19500 | 26000 | 26000 | 7800
Start Date | 2017-05-01 |  |  |  |  | 30 | 30 | 30 | 30 | 20 | 20 | 20
[6 empty] | Consultant | Consultant | Consultant | Consultant | Me | Me | Virtual Assistant | 137800
[5 empty] | Hourly Rate | 25 | 25 | 25 | 25 | 50 | 50 | 15 | 150
Iteration # | Iteration Goal | Product Increment # | Product Increment Goal | Start | End | UX Designer | Web App Developer | Mobile App Developer | Back End Web Developer | Product Owner | Scrum Master | Administrative Assistant | Total
1 |  | 0 | Team hired Development tools selected GitHub repository created Skeleton Web & Mobile Apps with User Registration/Log in Admin user setup Context configuration (School, Grade, Classroom). | 2017-05-01 | 2017-05-05 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
2 |  | 0 |  | 2017-05-08 | 2017-05-12 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
3 |  | 0 |  | 2017-05-15 | 2017-05-19 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
4 |  | 0 |  | 2017-05-22 | 2017-05-26 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
5 |  | 1 | Post homework information. | 2017-05-29 | 2017-06-02 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
6 |  | 1 |  | 2017-06-05 | 2017-06-09 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
7 |  | 1 |  | 2017-06-12 | 2017-06-16 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
8 |  | 1 |  | 2017-06-19 | 2017-06-23 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
9 |  | 1 |  | 2017-06-26 | 2017-06-30 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
10 |  | 2 | Online Calendar | 2017-07-03 | 2017-07-07 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
11 |  | 2 |  | 2017-07-10 | 2017-07-14 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
12 |  | 2 |  | 2017-07-17 | 2017-07-21 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
13 |  | 2 |  | 2017-07-24 | 2017-07-28 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
14 |  | 3 | Social Networking | 2017-07-31 | 2017-08-04 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
15 |  | 3 |  | 2017-08-07 | 2017-08-11 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
16 |  | 3 |  | 2017-08-14 | 2017-08-18 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
17 |  | 3 |  | 2017-08-21 | 2017-08-25 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
18 |  | 4 | Alerts and Notifications | 2017-08-28 | 2017-09-01 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
19 |  | 4 |  | 2017-09-04 | 2017-09-08 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
20 |  | 4 |  | 2017-09-11 | 2017-09-15 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
21 |  | 4 |  | 2017-09-18 | 2017-09-22 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
22 |  | 4 |  | 2017-09-25 | 2017-09-29 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
23 |  | 5 | School Pilot #1 Application adopted by 1 school. Configured for 1 classroom. Used by 2 teachers, 12 parents and 6 students (minimum). | 2017-10-02 | 2017-10-06 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
24 |  | 5 |  | 2017-10-09 | 2017-10-13 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
25 |  | 5 |  | 2017-10-16 | 2017-10-20 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
26 |  | 5 |  | 2017-10-23 | 2017-10-27 | 750 | 750 | 750 | 750 | 1000 | 1000 | 300 | 5300
Formulas:
Start = [Start, row above]+7
End = [Start]+4

## Resources Summary
1. Scrum Team
a. Product Owner | Interacts with end users and advisory board to uncover valuable features to include in our product. Maintains a prioritized list of features to be implemented by the Scrum Development Team.
Scrum Master | Plans and schedules feature implementation. Removes roadblocks.
UX Designer | Designs user experience for our application.
Web App Developer | Designs and implements the web-based clients.
Mobile App Developer | Designs and implements the mobile app clients
Cloud Developer | Designs and implements the back end and cloud based components of our solution.
2. Administrative Assistant | Handles scheduling and coordination of activities. Executes non-critical administrative tasks.
3. Advisory Board
Public School Administration Advisor | Advises on matters related to the adoption of our product by public schools.
Private School Administration Advisor | Advises on matters related to the adoption of our product by private schools.
School Teacher Representative(s) | Ensures that our product includes features of value to teachers.
Parent Representative(s) | Ensures that our product includes features of value to parents.
Student Representative(s) | Ensures that our product includes features of value to students.
Legal Advisor | Ensures that our product is in compliance with local and federal laws.

## Schedule Summary
Product Increment # | Weeks | Product Increment Goal
0 | 1 to 4 | Skeleton Web & Mobile Apps Registration and Context configuration
1 | 5 to 9 | Post homework information One to one messaging
2 | 10 to 13 | Automatic information classification and organization Group messaging
3 | 14 to 17 | Online Educational Calendar Social Networking
4 | 19 to 22 | Mobile Alerts & Notifications Document and multi-media attachments.
5 | 23 to 26 | School Pilot #1 Application adopted by 1 school. Used by 2 teachers, 12 parents and 6 students (minimum) in one classroom.

## Other Costs
24400
Computers | 3800
Dev Laptop #1 | 1000
Dev Laptop #2 | 1000
Mgmt Laptop #3 | 1000
Vitual Assistant Laptop | 800
Office Software | 2800
Office 365 + Storage | 300
Visio | 900
Other software | 1600
Web Hosting | 100
Hosting + Email | 60
Domain Names | 40
Operational Fees | 5500
Legal & Accounting | 680
Utilities | 1800
Transportation | 2280
Internet | 300
Phone | 300
MIscellaneous Fees | 140